SAMPLE PROJECT TIMETABLE

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **PROJECT PERIOD OF PERFORMANCE (POP) BY MONTH POST PERIOD**  **OF PERFORMANCE** | | | | | | | | | | | | | | |
| **ACTIVITY** | **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | **11** | **12** | **13** | **14** | **15** |
| Hire field assistant | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Purchase supplies, prepare for field season |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct monthly surveys | X | X | X | X | X | X | X | X | X | X | X | X |  |  |  |
| Conduct annual tree growth transect |  |  |  |  |  | X | X |  |  |  |  |  |  |  |  |
| Submit midterm financial and technical reports to USFWS (due within 30 days of the midterm of the project period of performance) |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |
| Community interviews |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |
| Submit final financial and technical reports to USFWS (due within 90 days of the end of the project period of performance) |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |
| Present results to host government, local communities |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |